LINDFIELD VILLAGE PLAN JOINT ADVISORY COMMITTEE

Progress Report No 3 on Implementing the Lindfield Village Plan

Background

The Lindfield Village Plan Joint Advisory Committee (LVPJAC) was jointly established by Lindfield Rural Parish Council and Lindfield Parish Council to oversee the implementation of the Lindfield Village Plan. The role of the LVPJAC is to seek the co-operation of the appropriate organisations so that the Action Points in the Village Plan are implemented; it is not responsible for carrying out the actual implementation. This is the LVPJAC’s third and final annual progress report.

In future monitoring the implementation of the Village Plan will be undertaken by the Lindfield and Scaynes Hill Action Plan Advisory Group. The latter will consist of representatives of the local community and the two parish councils and will meet in public.

Summary of Progress

Attached is a list of all the Village Plan Actions and the relevant supporting bullet points. The respective Actions and their supporting bullet points are shown in bold; the present position regarding their implementation is in italics.

The Village Plan contains twenty nine actions supported by eighty six bullet points; the report below shows progress or implementation has been achieved in respect of fifty-eight bullet points. Inevitably it has not been possible to make progress with some of the items. This is due to a variety of reasons including: insufficient funds being available (i.e. the lack of progress on extending the King Edward Hall), the responsible authority not being prepared to accept the need (i.e. failure to introduce a 40mph speed limit on the B2028 northern approach to Lindfield), or a lack of residents’ interest (i.e. in making greater use of Bluebird Transport).

Where after a bullet point “No further action to be taken” appears it means that the LVPJAC considers that at least one of the following applies:

- The Action point has been implemented

- As much of the Action point as the appropriate authority is likely to respond to has been

- The appropriate authority has declined to accept the Action point

- The appropriate bodies and/or local community has shown no interest in the Action point

- The appropriate authority has agreed to the Action point

- Circumstances have changed and it is accepted that the Action point is unlikely to be implemented

COMMUNICATIONS

ACTION 1:  TO INCREASE PROMOTION OF EVENTS & ACTIVITIES IN THE

VILLAGE

The Communications Forum for Lindfield continues to meet in order to co-ordinate the implementation of the communication actions. It is now under the  chairmanship of Alan Gomme.

No further action to be taken

- Review the provision and use of notice boards

A new notice board with map  has been installed  on the wall of Leaf and the existing notice boards are to be refurbished..

- Encourage clubs and societies to make use of village publication such

as Lindfield Times, Parish Council Newsletters, Lindfield Preservation

Society circulars and church publications to promote events and

recruit members

As a result of the publication of the Lindfield Times becoming erratic the   Communications Forum identified an alternative publisher willing to introduce a monthly magazine. As a result Lindfield Life was successfully launched in April 2009 and has been very well received and supported.

The two Parish Council newsletters are published in Lindfield Life.

Other organisations continue to produce their own newsletters solely for the benefit of their membership.

No further action to be taken

- Encourage greater use of the Parish Office as a source of information

The Neighbourhood Specialist Constable for Haywards Heath, continues to hold regular surgeries in the Parish Office.

As mentioned in the bullet point below the Parish Council’s web site is being updated which will give an opportunity to promote use of the Parish Office.

No further action to be taken

- Keep websites up to date

Lindfield Parish Council is in the process of revamping its website which will become more community based with Carolyn Nurse coordinating the latter aspects.

No further action to be taken

FACILITIES AND AMENITIES

ACTION 1:  TO PRESERVE A WIDE RANGE OF SHOPS

- Identify further adequate free parking.

No progress

- Encourage residents to use village shops.

No progress

- Publicise services and facilities available from existing businesses in village publications.

No progress

ACTION 2:  TO PROVIDE BETTER PUBLIC TOILET FACILITIES

- Retain and improve facilities in Denmans Lane

Achieved

- Reinstate toilet facilities in the area of the common

No progress

ACTION 3:  	TO INCREASE PROVISION OF SUITABLE SPACE FOR MEETINGS ETC. TO KEEP PACE WITH THE GROWTH IN VILLAGE SOCIAL ACTIVITIES.

- Extend King Edward Hall facilities

The proposed extension to the King Edward Hall has been indefinitely postponed as the Lindfield Club is not seeking to expand for the present. Without the latter making a financial contribution the extension is not viable.

- Seek additional accommodation

See above

ACTION 4:  TO ENCOURAGE VISITORS TO EXPLORE THE WHOLE

VILLAGE

- Display in the High Street area a village map showing pictorially places of interest

Councillors from LPC have tried to assist the Village Plan representatives in progressing this project but have reluctantly concluded that it is not possible to overcome a number of issues concerned with its design and location.

LPC does intend to include a street map of the village as part of the content of the extra notice board planned for the sidewall of “Leaf” in order to meet a separate requirement that has been identified by councillors.

No further action to be taken

- Continually updating the Lindfield Online website

In hand - see Communications fourth bullet point above

No further action to be taken

- Make existing promotional leaflets available in hotels and places of

interest outside Lindfield

No progress

ACTION 5:  TO RETAIN AND INCREASE POST OFFICE FACILITIES IN THE

VILLAGE

- Publicise services currently available

An article approved by the Postmaster entitled “More than Postage Stamps” was published in the Lindfield Times. The article set out the range of services available at the Lindfield Post Office and reminded residents of the need to “Use it or lose it”. This article was also the basis of a display by the LVPJAC on Village Day 2007.

No further action to be taken

- Liaise with Post Office for re-establishment of Post Office facilities away from village centre

With the closure of the Post Offices in Franklins Village and America Lane there would appear to be no hope of establishing facilities elsewhere in the village.

No further action to be taken

ACTION 6:  TO ENCOURAGE THE EXPANSION OF MEDICAL FACILITIES IN

THE CENTRE OF VILLAGE

- Support the present Practice

Improvements to existing medical centre facilities have been completed.

No further action to be taken

- Regularly monitor the situation

See above

No further action to be taken

HOUSING & ENVIRONMENT

ACTION 1:  TO PRESERVE HIGH STANDARDS IN ALL VILLAGE BUILDINGS

- Communicate to responsible authorities the importance of protecting our very special historic and architectural heritage.

See below

No further action to be taken

- Identify, in consultation with their owners, further buildings and structures for Listing.

No progress

- Carry out village-wide consultations on major planning proposals affecting the village as a whole.

The Lindfield Action Group (LAG) has been revived working together with the Lindfield Preservation Society (LPS, to meet the threat of major developments near Newton Road, and at other sites around the Village, arising from the Small Scale Housing Allocations and MSDC’s  Core Strategy Review.  There has been a considerable amount of work undertaken by the LPS and LAG in both making their own representations and in assisting the local community in doing likewise. Both of Lindfield’s Parish Councils have similarly been active in consulting with residents and making representations.

No further action to be taken

- Assist the owners and tenants of public buildings in the village to improve access opportunities for the elderly and less able.

No progress

ACTION 2:  TO PREPARE AND ISSUE A VILLAGE DESIGN STATEMENT

- Draw up the village design statement in accordance with the comprehensive guidelines set out by the Countryside Commission and with the agreement of the Local Planning Authority to inform Local Planning Policies

The public exhibition of the first draft of the Village Design Statement (VDS) took place at the King Edward Hall in November 2007.  Numerous constructive comments were received and a final draft together with a Sustainability Appraisal was been submitted to MSDC for the formal consultation process needed prior to approval.

Although all the local team fully appreciate the importance of achieving the approval of the VDS as an aid to protecting the Village in the face of pressures on MSDC to identify sites for more housing in the district,  unfortunately they were thwarted by MSDC’s initial inability to provide staff to undertaken their stage of the process. This has now been rectified and consultation is with MSDC is now taking place on preparing the draft ready for the final stage of consultation. This however will have delayed achieving final approval by at least twelve months.

ACTION 3:  TO ENSURE APPROPRIATE HOUSING FOR THE VILLAGE

- Press Mid Sussex District Council for high standards of design and construction in sympathy with existing buildings

See below

No further action to be taken

- Oppose new housing schemes without the provision of sufficient additional medical facilities and, where appropriate, schools

See below

No further action to be taken

- Oppose inappropriate large-scale housing developments

See below

No further action to be taken

- Resist proposals to build low-rise apartments by demolishing existing houses

The Parish Council and the Preservation Society continue to pursue this action and it’s supporting bullet points as individual planning applications come forward. Representations have been made to MSDC about their Core Strategy Pre-submission Document as a part of the actions to sustain housing standards and limit inappropriate development.

No further action to be taken

- Support initiatives to build affordable housing under conditions that ensure long-term affordable prices and rents.

This is considered by the Parish Council and Preservation Society on a scheme by scheme basis.

No further action to be taken

- Support initiatives to build more sheltered and very sheltered housing within easy reach of the village centre on suitable brown-field sites.

This is considered by the Parish Council and Preservation Society on a scheme by scheme basis.

No further action to be taken

#### ACTION 4:  TO RAISE STANDARDS IN THE LOCAL PLANNING PROCESS

- Inform Mid Sussex District Council of village opinions about the planning process as seen by applicants and others for both housing developments and trees.

See below

No further action to be taken

- Make constructive suggestions to the Parish and District Councils about improving the planning process.

The two Parish Councils and the Preservation Society continue to have a regular dialogue with each other and MSDC in order to improve the planning process.

No further action to be taken

ACTION 5:  TO MAINTAIN LINDFIELD AS A “BEST KEPT VILLAGE”

- Seek Volunteers to address issues raised by the Village Plan Questionnaire in a timely way, including young people interested in forming a band of “Lindfield Conservation Volunteers” similar to the Tree and Pond Wardens.

No progress

- Re-enter national and regional competitions to increase local interest and awareness.

The Lindfield Parish Council has raised this issue with various Village organisations but there has been no support.

No further action to be taken

- Support village initiatives to reduce air and noise pollution from traffic and other sources such as bonfires and garden machinery.

No progress

- Press responsible authorities for improved services to deal with overgrown roadside hedges, collection of dog waste, litter removal and green waste collection.

WSCC has introduced their “Ranger” scheme to the Village and this team is available every few weeks to undertake such items of maintenance as tackling overgrown hedges etc. These issues should be reported through the Parish Office.

MSDC is introducing a policy relating to dog owners and their responsibilities that should allow more effective enforcement of dog related regulations in the area.

LPC is investigating the replacement of all the litter bins in the village.

MSDC has successfully introduced the wheelie bin service for green waste, although it is recognised that this gives rise to other issues as a result of the proliferation of wheelie bins. The responsible authorities do respond to the other matters when they are drawn to their attention.

No further action to be taken

- Provide assistance to the elderly who need help with green waste removal.

MSDC do offer some assistance.

No further action to be taken

ACTION 6:  TO MAINTAIN ATTRACTIVE TREES & FLOWERS IN THE

VILLAGE

- Schedule prominent village trees under the guidance of the Tree Wardens and press for Tree Preservation Orders on trees identified as having public amenity value and at risk

See below

- Press for pollarding kerbside trees in High Street

Achieved

- Give publicity to Parish Council policy for flowers in public spaces

No progress

ACTION 7: TO MAINTAIN THE POND AS A HEALTHY AND ATTRACTIVE PUBLIC AMENITY

- Work with the Pond Warden to develop and publicise guidelines to improve the health of the pond, including the installation of public notices about feeding wild-fowl and consider a scheme to make suitable bird-feed available.

LPC has installed two information boards about the pond and in particular about not feeding the ducks with inappropriate foods.

- Action appropriate issues raised in the Village Plan Questionnaire.

No progress

- Develop and implement a better pond aeration system.

MSDC have been advised of the current failure of the aeration system in the pond.

- Collaborate with the responsible authorities to protect the long-term physical integrity of the pond, and to ensure periodic pond cleaning and maintenance.

MSDC, who are responsible for the Common including the Pond, has consulted with many parties including LPC and the Pond Warden about a new management policy for the pond. This has now been published and implemented.

No further action to be taken

SAFETY & SECURITY

ACTION 1: TO REDUCE ANTI-SOCIAL BEHAVIOUR

- Enhance communication with the police and other relevant authorities

The Neighbourhood Specialist Constable for Haywards Heath now holds regular surgeries in the Parish Office.

No further action to be taken

- Encourage residents to report all incidents, as Police records only take account of reported incidents

See comments under first bullet point above.

Streetmate continues to have a regular presence in the Village and respond to incidents of anti-social behaviour involving young people.

No further action to be taken

ACTION 2:  TO RESTORE AND EXPAND NEIGHBOURHOOD WATCH

THROUGHOUT THE VILLAGE

- Recruit Neighbourhood Watch Co-ordinators with the aim of achieving total street coverage

See below

- Improve communication between the Police and all levels of Neighbourhood Watch Volunteers

It continues to be difficult to obtain accurate information about the level of active Neighbourhood Watch coverage in the Village which at best seems to be patchy.

ACTION 3:  TO ACHIEVE A UNIFORM STANDARD OF LIGHTING

THROUGHOUT THE VILLAGE

- Institute an inspection procedure for all existing public-owned lighting

The public lighting which is the responsibility of the Parish Council is inspected fortnightly for “outages” and cleaned annually. The remainder of the public lighting is the responsibility of WSCC and this is inspected fortnightly for “outages” in the winter and monthly during the summer; it is cleaned every two years. In addition last year a representative of WSCC together with two parish councillors and the Parish Clerk undertook a survey of all WSCC’s lighting in the Village.

No further action to be taken

- Ensure contractors are systematically advised of malfunctions or when lights are obscured by trees or hedges.

See first bullet point above and fifth bullet point of Action 4.

No further action to be taken

- Upgrade lighting where and when appropriate

This takes place as appropriate

No further action to be taken

- Install additional lighting where considered necessary and when finance is available

The Lighting Working Group considers requests for extra lighting.

No further action to be taken

- Encourage Neighbourhood Watch Street Co-ordinators and residents to report problems, especially where street lighting is obscured.

Re Neighbourhood Watch Co-ordinators there has been a lack of progress generally, see Action 2 second bullet point above. The Parish Office encourages residents to either report issues directly to the appropriate authority or does so on their behalf.

No further action to be taken

ACTION 4:  SAFETY AND MAINTENANCE OF FOOTPATHS AND

PAVEMENTS

- Make regular inspections to identify obstructions on pavements.

See below

No further action to be taken

- Regularly trim back public and private hedging that impedes access to footpaths and pavements.

See below

No further action to be taken

- Ensure hedges and trees do not obstruct street lighting and road signage and driver and pedestrian sight lines.

See below

No further action to be taken

- Report damage and unevenness of pavements and tactile paving that might cause accidents.

See below

No further action to be taken

- Minimise random car parking on pavements and verges.

Lindfield Parish Council introduced a system of sector patrols which has improved the flow of information about the issues listed above. These are then drawn to the attention of the responsible authority.

No further action to be taken

SPORT & LEISURE

ACTION 1: TO PROVIDE BETTER FACILITIES FOR THE YOUNGER AGE

GROUPS

- Provide more meeting places for young people

Achieved - since the drafting the Village Plan the Albermarle Centre at Oathall 	Community College has been revamped and provides a lively meeting place for young people.

No further action to be taken

- Give increased support to Streetmate

LVPJAC has been actively involved in assisting Streetmate with its drive to

secure its funding. A member of the LVPJAC has joined Streetmate’s Management Committee and has been given the lead on applying for grants.  Contributions have been secured from Lindfield Preservation Society, Lindfield Parish Council, Cuckfield and Lindfield Rotary, Mid Sussex Crime and Disorder Reduction Partnership and West Sussex County Council..

No further action to be taken

- Provide for a multi-purpose outdoor all-weather playing surface and skate board area. This could be used for informal practice and training for many sports particularly during adverse weather when grass areas are unsuitable

No progress

##### Continue the ongoing discussions with local schools and explore what facilities could be utilised more

No progress

- Approach local clubs to step-up their profiles, particularly to the younger age groups

Last year it was anticipated that this would form an important part of the role of the local community editor for Lindfield Online. The aim being for the potholder to become the hub of a flow of up-to-date information from local clubs and organisations about opportunities and events, and to promote the linking of all local websites to Lindfield Online. Letters were sent to all local organisations promoting this initiative. With the demise of Lindfield Online referred to in the Communications section above, this role will have to wait the launching of the revamped Parish Council web site.

ACTION 2:  TO GIVE LOCAL YOUTH A VOICE THROUGH A LINDFIELD

YOUTH COUNCIL

- Establish a Youth Council with the support of the Lindfield Parish and the involvement of all relevant local youth bodies

A Local Youth Forum covering Haywards Heath and the surrounding area has been established.

No further action to be taken

ACTION 3:  TO IMPROVE ACCESS TO SPORT AND LEISURE FACILITIES

- Consider the options for making it easier for people with disabilities to be brought to King Edward Hall by vehicle.

No progress has been made on this issue and it seems doubtful that it will be.

- Promote car-sharing and “lift offer” schemes.

This is a matter for the individual organisations using the hall.

No further action to be taken

- Promote greater use of Bluebird Transport.

This was piloted by the Lindfield Preservation Society but was found to be uneconomic due to the low and unreliable level of use.

No further action to be taken

TRAFFIC & TRANSPORT

ACTION 1:	TO IMPROVE THE LEWES ROAD/HIGH STREET JUNCTION

- Install a mini-roundabout

Agreed but not yet implemented.

No further action to be taken

ACTION 2:	TO IMPLEMENT TRAFFIC MANAGEMENT & CALMING

MEASURES

- Introduce measures to reduce speed and to discourage through traffic in Hickmans Lane & Sunte Avenue, with complementary measures in Finches Park Road & By Sunte if necessary.

Lindfield Parish Council has placed this issued on the LTSJWP agenda for consideration but to date there has been no progress.

- Initiate actions to reduce through traffic in Eastern Road, Luxford Road, Newton Road, Dukes Road and Brushes Lane.

Lindfield Parish Council has placed this issue on the LTSJWP agenda and it has been agreed that the problems will be re-evaluated once the impact of the High Street/Lewes Road mini-roundabout and/or Newton Road development are known.

- Implement enhanced measures to increase driver awareness of the West Common/Appledore Gardens mini-roundabout and investigate speed reduction measures for West Common.

Completed

- Introduce a 40mph speed limit on the B2028 northern approach from Hollyrood on Buxshalls Hill to the Lindfield gateway.

The issue is again being pursued by Lindfield Rural Parish Council following revised D of T guidelines on speed limits.  This traffic calming measure has been discussed and is supported by LTSJWP.

- Implement effective calming measures at or inside key gateways into Lindfield.

- B2111

- B2028 West Common

Calming measures on the B2111 at Scamps Hill and Lewes Road and the B2028 West Common formed part of the agreed Route Speed Management scheme and have been implemented.  These broadly address the Village Plan concerns.

- C10 High Beeches / Summerhill Lane

Regarding the C10 following consideration it was decided by WSCC that additional calming measures were not warranted.  The LVPJAC initially accepted this decision but now consider calming should be further investigated due to the high level of non compliance with the speed limit as evidenced by Lindfield Community Speedwatch and this was supported by LTSJWP at their spring 2009 meeting.

- B2028 northern gateway

Calming measures inside the northern gateway on the B2028 have been discussed within the LTSJWP.  It has been indicated by WSCC that roundels supporting the 30mph signs could be provided and this would be considered if requested by the Parish Council.

- Gravelye Lane

Measures for Gravelye Lane have not been actively pursued as there appears to have been little support or chance of success.

ACTION 3:	TO REDUCE PEDESTRIAN – VEHICLE CONFLICT

- Build up kerb and pavement at entrance to Lewes Road to

Discourage vehicle overrun

WSCC are understood to be considering this issue in conjunction with the junction improvement.

- Provide surface treatment and associated measures to protect pedestrian space at eastern end of Hickmans Lane to High Street.

This has received little support from Lindfield Parish Council.  It was recently discussed by LTSJWP and agreed that further consideration should be given.

- Provide appropriate pedestrian crossing points in:

- Central High Street [below Alma Road]

This action point was initially left in abeyance pending resolution of High Street parking proposals and is not currently being pursued pending outcome of proposed pedestrian crossing in High Street near Lewes Road junction.

- Lower High Street [near Pondcroft Road]

Implemented as part of the WSCC Route Speed Management scheme.

- Lewes Road [East of Old School Court and/or near Noah’s Ark Lane]

Implemented as part of the WSCC Route Speed Management scheme

- Summerhill Lane [near school]

Has been considered and rejected by WSCC.

- Provide pedestrian island refuge in Westlands Road at junction with Gravelye Lane

This Action Point has not been pursued due to lack of support and insufficient grounds to justify the enhancement.

ACTION 4:	TO MONITOR THE PERFORMANCE AND EFFECT OF PARKING    	          ENFORCEMENT

- Assess and pursue effective local authority parking enforcement.

Implemented but position should continue to be monitored by Lindfield Parish Council on an ongoing basis.

- Review impact and assess further parking measures and provisions required

A review will be required by Lindfield Parish Council when currently outstanding parking restrictions have been implemented.

ACTION 5:	TO INVESTIGATE FEASIBILITY OF INTRODUCING A 20MPH

SPEED LIMIT AND HEAVY GOODS VEHICLE RESTRICTIONS

IN LINDFIELD

- Investigate the feasibility of introducing a 20 mph zone within the

five entry points to Lindfield village, or at least in the vicinity of

schools

- Investigate HGV ‘access only’ restrictions for Hickmans Lane & Sunte Avenue, Lewes Road and High Street

Whilst these are a valid Actions they has not been pursued as funding for a feasibility study and subsequent  possible implementation was perceived as being unavailable.  However Actions 1 to 3 contribute towards managing driver speeds and vehicle volumes within Lindfield.

ACTION 6:	TO REDUCE SCHOOL RUN TRAFFIC THROUGH THE EFFECTIVE IMPLEMENTATION AND PROMOTION OF

SCHOOL TRAVEL PLANS

- Encourage active parent participation in the delivery of the Lindfield Primary, Blackthorns and Oathall school travel plans TOGETHER WITH SUPPORT FOR THE ‘Safer Routes to School’ initiative

This action has yet to be considered but remains a valid objective for Lindfield Parish Council to pursue.  Currently Lindfield Parish Council are considering drop off and pick up parking issues in the vicinity of Blackthorns School.

ACTION 7:	TO LOBBY BUS OPERATORS TO PROVIDE ENHANCED

SERVICES

- Provide route information and timetables at bus stops

New timetable holders have been provided at bus stops by Lindfield Parish Council.

- Seek improved routes and service hours

These is considered to be unrealistic in the current climate but could be considered further as contributing to sustainability if any of the proposed housing developments take place.

- Investigate innovative solutions to increase bus usage

Since the Village Plan was agreed a national scheme for free over 60s bus travel has been introduced, accordingly further action was considered inappropriate at the present time.

ACTION 8:	TO ENCOURAGE CYLING FOR SHORT JOURNEYS

- Provide lockable cycle parking facilities in central Lindfield and on the Common

MSDC are understood to be considering facilities for Toll Gate car park.  The justification for facilities on the Common are very limited.

- Actively support West Sussex and Central Mid Sussex Area transport plans for safe cycle routes and promote the inclusion of the Lindfield area in any network

There are currently no known plans for cycle routes in the Lindfield area, accordingly this Action Point has not been pursued.